## Sheet1
ID | Story ID | Story Name | Short Description/ Task | Story # and details | Spring Cycle Number | Resources working | Hardware or Software | Progress
1 | 1 | Home page | Set up Github & add all developers | Story 1, Paragraph 1 | 1 | Kimani Guchu | software | complete
2 | 1 | Home page | Create Project description & deciding prefered languages | Story 1, Paragraph 1 | 1 | All Members | software | complete
3 | 1 | Home page | Decide what information to include on Homepage | Story 1, Paragraph 2 | 1 | Aboubaker Sherif, Ri Joo | software | complete
4 | 1 | Home page | Challeges faced during during building the software and how can we solve it. | Story 1, Paragraph 1 | 1 | Mohammed Altamash, Kimani Guchu | software | complete
5 | 1 | Home page | Decide on navigation bar links & destinations. | Story 1, Paragraph 3 | 1 | Saahajm | software | complete
6 | 1 | Home page | Determine what content/images to include on the homepage | Story 1, Paragraph 2 | 1 | Kimani Guchu | software | complete
7 | 1 | Home page | Design the layout of the homepage | Story 1, Paragraph 2 | 1 | Ri Joo | software | Complete
8 | 2 | Business Page | 2.1: Create layout for dropdown menu. | Story 2, Paragraph 2 | 2 | Kimani Guchu | software | complete
9 | 2 | Business Page | 2.2: Create a Business / Cooperation marketing page. | Story 2, Paragraph 2 | 2 | Ri Joo, Saahajm | software | complete
10 | 2 | Business Page | 2.3: Source information about the security of modern security cameras/surveillance systems. | Story 2, Paragraph 3 | 2 | Mohammed Altamash | software | complete
11 | 2 | Business Page | 2.4 Create / Write content to be included on the business/corporations page. | Story 2, Paragraph 3 | 2 | Aboubaker Sherif | software | Complete
12 | 3 | Mobile app | 3.1 Create a installation link for mobile app. | Story 3, Paragraph 2 | 3 | Mohammed Altamash | software | In Progress
13 | 3 | Mobile app | 3.2 Design the mobile app version | Story 3, Paragraph 2 | 3 | Kimani Guchu | software | In Progress
14 | 3 | Mobile app | 3.3 Construct the mobile app | Story 3, Paragraph 2 | 3 | Saahajm , Ri Joo | software | In Progress
15 | 3 | Mobile app | 3.4 Create the content the custumer can check the update version and update to latest. | Story 3, Paragraph 3 | 3 | Aboubaker Sherif | software | In Progress
16 | 4 | Storage | 4.1 Create a database in order to store user information. | Story 4, Paragraph 3 | 4 | Saahajm | software | Not Complete
17 | 4 | Storage | 4.2 implement interface to determine if user wants to save data directly to their device and where to save on their device. | Story 4, Paragraph 3 | 4 | Ri Joo , Aboubaker Sherif | software | Not Complete
18 | 4 | Storage | 4.3 Determine how to encoportate cloud storage for recordings | Story 4, Paragraph 3 | 4 | Mohammed Altamash | software | Not Complete
19 | 4 | Storage | 4.4 create notifications for when customers cloud storage is getting close to full | Story 4, Paragraph 3 | 4 | Kimani Guchu | software | Not Complete

## Sheet2
Story ID | Story Description | Task ID | Task Description | Assumptions
1 | William is a home owner trying to find the safest way to secure his home. He is browsing the web and comes across our product site, he is brought to the homepage which demonstrates the concept of how our product works, aswell as its many utilities. He scrolls down the homepage where he is presented with safety statistics and content based promoting our latest surveillance software technology. William then clicks the homeowner tab where he is presented with residential product information, pricing and installation details. | 1 | 1.1 Decide on navigation bar links & destinations. 1.2 Determine what content/images to include on the homepage 1.3 Design the layout of the homepage 1.4 Decide what information to include on Homepage | The customer will stay on our website long enough to scroll through the informational content, he will then proceed to the "homeowner" section which will further detail product characteristics that specifically apply to them.
2 | Jannet is a business owner searching for a better way to protect her store during the night. She comes across our website and browses the homepage where she's presented with information details about our software. If she clicks the navigation bar on the side of the page she is presented various options including a Business/Cooperation tab. She is then led to a page that details how our surveillance system can be set up to monitor businesses remotely with little ways of tampering due to the drones flight, as compared to regular mounted security cameras. | 2 | 2.1: Create layout for the dropdown menu. 2.2: Create a Business / Cooperation marketing page. 2.3: Source information about the security of modern security cameras/surveillance systems. 2.4 Create / Write content to be included on the business/corporations page. | The customer will view our site long enough to navigate to the "menu" in which she will find corresponding subsections. The client will click the business tab which will lead her to a seperate page that details the use of our product in a professional / corporate setting. she will then view the promotional content provided on the page
3 | Bryan is a correctional officer tracking the criminals for preventing abnormal behaviors and motions. He needs to download this software on the portable devices to monitor the system everywhere. Mobile version and PC version of the software can have problem and software needs to keep updated or they could not sync properly. If he check the version of the software, he can update to latest version. |  | 3.1 Create a installation link for mobile app. 3.2 Design the mobile app version 3.3 revise the hompage layout to looks simple on mobile app. 3.4 Create the content the custumer can check the update version and update to latest. | The customer will also able to install and use on the mobile application version.
4 | Daisy runs a parking deck in downtown Atlanta where there are constantly cars going in and out but the area is not the safest place. She needs to be able to go back & foward in the recording of the what happens in the lot, in case of car crashes or theft. For this to be possible, Daisy can either save the footage on her devices or she can store the recordings in the cloud, up to a certain amount of storage is provided so she has easy access to any recordings from the software. | 4 | 4.1 Create a database in order to store user information. 4.2 Let customer decide if they would like to save data directly to their device and where to save on their device. 4.3 Let customer decide how much cloud storage they would like to have on their account. 4.4 Send notifications when the customers cloud storage is getting close to full | The customer will have full transparency with the software to have full control over their decisions and preferences with downloading/saving past footage.
5

## Sheet3
Spring Cycle # 3 | Start : 10/12/2022 | End : 10/30/2022
Project Team # 1
Team Lead: Kimani Guchu
Task ID | Task Description | Task Owner | Duration of the task in Days | Task Due date | Task Progress Complete % | Reminder Sent (Y/N) | Ack. By Task owner | Criticalty (High, Medium, Low) | Comments
1 | Create the home page for website | Ri Joo , Kimani Guchu, Mohammed Altamash | 12 | 2022-10-30 | 90% | Y | Y | High | We are collectively working on everything as a group. The people in the group that are better at coding websites and using HTML are focused more on the web pages.
2 | Create the business page for the website | Mohammed Altamash , Aboubaker Sherif | 14 | 2022-11-06 | 75% | Y | Y | Medium | The people in the group that are better at coding websites and using HTML are focused more on the web pages. We consulted as a group and came to a decision for design and what to include.
3 | Create the mobile app for the surveillance drone | Saahajm, Kimani Guchu, Ri Joo | 25 | 2022-11-20 | 25% | Y | Y | High | Similar to the other tasks we are collectively working on this as a group. We have some people in the group who took mobile app development and they decided to take more of a lead for this task. We are all still fairly new to this so we are learning as we go.
4 | Create database & local for storage recordings from the drone | Aboubaker Sherif, Saahajm | 32 | 2022-11-27 | 10% | Y | N | Medium | Last task we have is creating a database to store recordings. None of us have much experience if any working with databases so we are doing our best as a group to finish this task. We are all working on all parts together but some taking more of a lead in certain parts then others.